## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | KONGRUL İŞ-ZAMAN GRAFİĞİ
Enter Company Name in cell B2. | Proje Başlangıç Tarihi: 01.02.2022
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Proje Bitiş Tarihi: 09.08.2022
| Takım Danışmanı: Burak YILMAZ |  |  | AYLAR
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | Takım Kaptanı: Yunus Emre GÜÇLÜ |  |  | ŞUBAT | MART | NİSAN | MAYIS | HAZİRAN | TEMMUZ | AĞUSTOS
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | GÖREVLER | SORUMLU KİŞİLER | DAYS
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Senaryo belirleme, algoritma geliştirme ve raporlama |  | #REF!
| Fikir Geliştirme | Tüm Üyeler | #REF!
| Mekanik tasarım geliştirme | Tüm Üyeler | #REF!
| Aviyonik tasarım geliştirme | Bekir Burak Çelik , Mehmet Samet Işık,Yunus Emre Güçlü | #REF!
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Kullanılacak yazılımların tespiti, tasarlanması ve geliştirilmesi | Batuhan Yorul | #REF!
| Raporlama | Tüm Üyeler | #REF!
| Gerekli malzemelerin tespiti ve temini |  | #REF!
| Aviyonik tasarım kesinleştirme | Bekir Burak Çelik , Mehmet Samet Işık | #REF!
| Mekanik tasarım kesinleştirme | Kerem Kuzgun | #REF!
Sample phase title block | Mekanik ve aviyonik tasarım için gereken malzemelerin tespiti | Kerem Kuzgun, Mehmet Samet Işık | #REF!
| Malzemelerin temini | Yunus Emre Güçlü | #REF!
| IHA yapımımına başlangıç |  | #REF!
| Ana İHA Yapımı ve hata ayıklama | Kerem Kuzgun, Mehmet Samet Işık, Bekir Burak Çelik | #REF!
| Malzemelrin kalitesini kontrol etme | Mehmet Samet Işık , Yunus Emre Güçlü | #REF!
| Bebek İHA Yapımı ve hata ayıklama | Kerem Kuzgun, Mehmet Samet Işık, Bekir Burak Çelik | #REF!
Sample phase title block | Yer istasyonu tasarımı ve sistem uyumluluğu testi | Mehmet Samet Işık , Batuhan Yorul | #REF!
| İHA’ların entegrasyonu | Yunus Emre Güçlü , Batuhan Yorul , Mehmet Samet Işık | #REF!
| Sistem uyumluluk testleri |  | #REF!
| Ana IHA uçuş testleri | Tüm Üyeler | #REF!
| Bebek İHA uçuş testleri | Tüm Üyeler | #REF!
| Ana IHA ve bebek IHA arası veri alışverişi testleri | Tüm Üyeler | #REF!
This is an empty row | Yer istasyonu yeterlilik testi | Tüm Üyeler | #REF!
| Bütünleşmiş sistem testleri | Tüm Üyeler | #REF!
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)
□(64&1/4)
□(64&2/4)
□(64&3/4)
□(64&4/4)